## Index
QA TESTER | Tim QA |  | APP | CCTV Dashboard Web App
DATE TESTED | 2026-06-04 |  | PLATFORM | Web Browser (Chrome/Firefox)
Dokumen ini berisi checklist Quality Assurance dan Testing Engineer untuk semua fitur di aplikasi CCTV Dashboard Monitoring.
Setiap fitur memiliki test cases prioritas dan status tracking.
#PRIORITY LEGEND / TANDA PRIORITAS |  |  |  | ## Notes & Observations
Priority | Meaning | Test When |  | - Testing Environment:
P0 | Critical - Must test before any release | Every build |  | - Platform: Web Browser (Chrome, Firefox, Edge)
P1 | High - Important flows | Every release |  | - Build: Development / Staging
P2 | Medium - Secondary flows | Weekly/Regression |  | - Test Data Requirements:
P3 | Low - Nice to have | Monthly/Major release |  | - At least 1 tenant/company registered
- At least 2 users (owner & member)
#STATUS LEGEND / TANDA STATUS |  |  |  | - At least 2 cameras configured
Status | Meaning |  |  | - At least 5 identities (face data) in database
11036 | ⬜ Not started |  |  | - At least 10 historical events/incidents
🔄 | 🔄 In progress
✅ | ✅ Passed
❌ | ❌ Failed - Bug found
⏸️ | ⏸️ Blocked

## Feature Test
Test ID | Feature | Test Case | Priority | Status | Bug Reference | Notes | Tester | Date Tested | Result Notes
AUTH-001 | Authentication - Login | Login dengan email & password valid | P0 | ⬜ Not started |  | Happy path - redirect ke dashboard
AUTH-002 | Authentication - Login | Login dengan email tidak terdaftar | P0 | ⬜ Not started |  | Expect error message tampil
AUTH-003 | Authentication - Login | Login dengan password salah | P0 | ⬜ Not started |  | Expect error message tampil
AUTH-004 | Authentication - Login | Login dengan email format invalid | P1 | ⬜ Not started |  | e.g. bukan-email
AUTH-005 | Authentication - Login | Login dengan field email & password kosong | P1 | ⬜ Not started |  | Validasi field kosong
AUTH-006 | Authentication - Login | Toggle show/hide password berfungsi | P2 | ⬜ Not started |  | Icon berubah, password visible/hidden
AUTH-007 | Authentication - Login | Remember Me / session persist setelah tab ditutup | P1 | ⬜ Not started |  | Session masih aktif saat buka kembali
AUTH-008 | Authentication - Login | Link ke Forgot Password berfungsi | P2 | ⬜ Not started |  | Navigasi ke halaman reset password
AUTH-009 | Authentication - Login | Redirect ke dashboard jika sudah login | P0 | ⬜ Not started |  | Tidak perlu login ulang
AUTH-010 | Authentication - Login | Loading state saat proses login | P2 | ⬜ Not started |  | Button disabled, spinner visible
AUTH-020 | Authentication - Sign Up | Sign up sebagai Owner dengan data valid (Step 1 Personal Data) | P0 | ⬜ Not started |  | Nama, email, password lengkap
AUTH-021 | Authentication - Sign Up | Sign up Step 2 Company Data - isi data perusahaan valid | P0 | ⬜ Not started |  | Nama perusahaan, deskripsi, dsb
AUTH-022 | Authentication - Sign Up | Sign up dengan email sudah terdaftar | P0 | ⬜ Not started |  | Expect error message duplikat email
AUTH-023 | Authentication - Sign Up | Sign up dengan password tidak match (confirm password) | P1 | ⬜ Not started |  | Validasi konfirmasi password
AUTH-024 | Authentication - Sign Up | Sign up dengan password terlalu pendek (<6 karakter) | P1 | ⬜ Not started |  | Min 6 karakter Supabase default
AUTH-025 | Authentication - Sign Up | Sign up dengan email format invalid | P1 | ⬜ Not started |  | Validasi format email
AUTH-026 | Authentication - Sign Up | Sign up dengan field wajib kosong | P1 | ⬜ Not started |  | Semua field required tervalidasi
AUTH-030 | Authentication - Sign Up (Invite) | Sign up sebagai Member dengan invite code valid | P0 | ⬜ Not started |  | Step 2 invite code path
AUTH-031 | Authentication - Sign Up (Invite) | Sign up dengan invite code tidak valid / expired | P0 | ⬜ Not started |  | Expect error message jelas
AUTH-032 | Authentication - Sign Up (Invite) | Sign up dengan invite code kosong | P1 | ⬜ Not started |  | Validasi field invite code
AUTH-040 | Authentication - Forgot Password | Reset password dengan email terdaftar | P0 | ⬜ Not started |  | Email reset dikirim, pesan sukses tampil
AUTH-041 | Authentication - Forgot Password | Reset password dengan email tidak terdaftar | P1 | ⬜ Not started |  | Check error handling - jangan expose info
AUTH-042 | Authentication - Forgot Password | Reset password dengan email format invalid | P2 | ⬜ Not started |  | Validasi format email
AUTH-043 | Authentication - Forgot Password | Loading state saat submit | P2 | ⬜ Not started |  | Button disabled saat proses
AUTH-050 | Authentication - Logout | Logout dari navbar/profile | P0 | ⬜ Not started |  | Redirect ke halaman login
AUTH-051 | Authentication - Logout | Session cleared setelah logout | P0 | ⬜ Not started |  | Tidak bisa akses halaman protected
AUTH-052 | Authentication - Logout | Protected route redirect jika tidak login | P0 | ⬜ Not started |  | Redirect ke /login jika belum auth
MON-001 | Live Monitoring | Halaman monitoring tampil setelah login | P0 | ⬜ Not started |  | Camera grid ter-render
MON-002 | Live Monitoring | Camera feed streaming berjalan (MJPEG) | P0 | ⬜ Not started |  | Stream aktif dari kamera yang running
MON-003 | Live Monitoring | Camera offline menampilkan state error/offline | P1 | ⬜ Not started |  | Placeholder atau pesan offline
MON-004 | Live Monitoring | Grid layout dapat diubah (1x1, 2x2, 3x3, dst) | P1 | ⬜ Not started |  | Layout selector berfungsi
MON-005 | Live Monitoring | Event deteksi wajah tampil secara real-time | P0 | ⬜ Not started |  | Event muncul via WebSocket tanpa refresh
MON-006 | Live Monitoring | Notifikasi event baru muncul di notification dropdown | P1 | ⬜ Not started |  | Badge count update real-time
MON-007 | Live Monitoring | Filter event berdasarkan kamera | P1 | ⬜ Not started |  | Hanya event kamera terpilih yang tampil
MON-008 | Live Monitoring | Filter event berdasarkan severity/status | P1 | ⬜ Not started |  | Filter violation/compliance/unknown
MON-009 | Live Monitoring | Stream quality selector berfungsi | P2 | ⬜ Not started |  | Pilihan kualitas stream berubah
MON-010 | Live Monitoring | Halaman tetap stabil saat banyak kamera aktif | P1 | ⬜ Not started |  | Tidak ada memory leak atau crash
MON-011 | Live Monitoring | Realtime event tidak duplikat | P1 | ⬜ Not started |  | Event hanya muncul sekali
MON-012 | Live Monitoring | Koneksi WebSocket reconnect saat terputus | P1 | ⬜ Not started |  | Auto-reconnect setelah disconnect
HIS-001 | Incident History | Daftar event/incident tampil dengan benar | P0 | ⬜ Not started |  | Data dari database terload
HIS-002 | Incident History | Pagination event berfungsi | P1 | ⬜ Not started |  | Next/prev page berfungsi
HIS-003 | Incident History | Search event berdasarkan keyword | P1 | ⬜ Not started |  | Filter hasil sesuai keyword
HIS-004 | Incident History | Filter event berdasarkan tanggal (date range) | P1 | ⬜ Not started |  | Range tanggal start-end berfungsi
HIS-005 | Incident History | Filter event berdasarkan kamera | P1 | ⬜ Not started |  | Dropdown kamera filter berfungsi
HIS-006 | Incident History | Filter event berdasarkan status (violation/compliance) | P1 | ⬜ Not started |  | Filter status event
HIS-007 | Incident History | Detail event dapat dibuka (foto evidence, info) | P1 | ⬜ Not started |  | Modal/halaman detail event
HIS-008 | Incident History | Review event - mark sebagai violation | P0 | ⬜ Not started |  | Status event berubah & tersimpan
HIS-009 | Incident History | Review event - mark sebagai valid/compliance | P0 | ⬜ Not started |  | Status event berubah & tersimpan
HIS-010 | Incident History | Export event history sebagai CSV | P1 | ⬜ Not started |  | File CSV terdownload dengan data lengkap
HIS-011 | Incident History | Empty state jika belum ada event | P2 | ⬜ Not started |  | Tampilkan pesan/ilustrasi empty
HIS-012 | Incident History | Loading state saat fetch data | P2 | ⬜ Not started |  | Spinner/skeleton loading tampil
IDN-001 | Identity Management | Daftar identitas (staf) tampil | P0 | ⬜ Not started |  | Data wajah dari database
IDN-002 | Identity Management | Tambah identitas baru dengan data valid | P0 | ⬜ Not started |  | Nama, departemen, foto wajah
IDN-003 | Identity Management | Upload foto wajah untuk identitas | P0 | ⬜ Not started |  | Foto berhasil diupload ke storage
IDN-004 | Identity Management | Edit data identitas yang sudah ada | P1 | ⬜ Not started |  | Perubahan tersimpan ke database
IDN-005 | Identity Management | Hapus identitas | P1 | ⬜ Not started |  | Konfirmasi hapus, data terhapus
IDN-006 | Identity Management | Trigger face encoding setelah upload foto | P0 | ⬜ Not started |  | Backend memproses encoding wajah
IDN-007 | Identity Management | Validasi field wajib identitas (nama minimal) | P1 | ⬜ Not started |  | Error jika field kosong
IDN-008 | Identity Management | Filter/search identitas berdasarkan nama | P2 | ⬜ Not started |  | Hasil filter sesuai keyword
IDN-009 | Identity Management | Upload foto format tidak valid (bukan JPG/PNG) | P1 | ⬜ Not started |  | Error message format tidak didukung
IDN-010 | Identity Management | Empty state jika belum ada identitas | P2 | ⬜ Not started |  | Tampilkan pesan empty
IDN-011 | Identity Management | Foto preview tampil setelah upload | P2 | ⬜ Not started |  | Preview foto sebelum save
CAM-001 | Camera Management | Daftar kamera tampil | P0 | ⬜ Not started |  | Data kamera dari database
CAM-002 | Camera Management | Tambah kamera baru dengan data valid | P0 | ⬜ Not started |  | Nama, URL stream, lokasi
CAM-003 | Camera Management | Edit data kamera yang sudah ada | P1 | ⬜ Not started |  | Perubahan tersimpan
CAM-004 | Camera Management | Hapus kamera | P1 | ⬜ Not started |  | Konfirmasi hapus, kamera terhapus
CAM-005 | Camera Management | Start stream kamera | P0 | ⬜ Not started |  | Status kamera berubah menjadi aktif
CAM-006 | Camera Management | Stop stream kamera | P0 | ⬜ Not started |  | Status kamera berubah menjadi offline
CAM-007 | Camera Management | Validasi URL stream kamera (format RTSP/HTTP) | P1 | ⬜ Not started |  | Error jika format URL salah
CAM-008 | Camera Management | Status kamera update real-time | P1 | ⬜ Not started |  | Status online/offline update tanpa refresh
CAM-009 | Camera Management | Grid layout kamera dapat dipilih | P2 | ⬜ Not started |  | Layout selector berfungsi
CAM-010 | Camera Management | Tambah kamera dengan field wajib kosong | P1 | ⬜ Not started |  | Validasi error tampil
REP-001 | Reports | Halaman reports tampil dengan data | P0 | ⬜ Not started |  | Laporan event dengan foto evidence
REP-002 | Reports | Filter report berdasarkan tanggal | P1 | ⬜ Not started |  | Hasil sesuai range tanggal
REP-003 | Reports | Filter report berdasarkan kamera | P1 | ⬜ Not started |  | Hasil sesuai kamera dipilih
REP-004 | Reports | Foto evidence tampil di report | P0 | ⬜ Not started |  | Gambar ter-load dari storage
REP-005 | Reports | Detail report dapat dibuka | P1 | ⬜ Not started |  | Info lengkap event tampil
REP-006 | Reports | Pagination report berfungsi | P1 | ⬜ Not started |  | Next/prev page berfungsi
REP-007 | Reports | Empty state jika tidak ada report | P2 | ⬜ Not started |  | Pesan/ilustrasi empty
REP-008 | Reports | Loading state saat fetch report | P2 | ⬜ Not started |  | Spinner tampil saat loading
SET-001 | Settings | Halaman settings tampil | P0 | ⬜ Not started |  | Konfigurasi workspace
SET-002 | Settings | Lihat dan generate invite code | P0 | ⬜ Not started |  | Invite code bisa di-generate & di-copy
SET-003 | Settings | Revoke/nonaktifkan invite code | P1 | ⬜ Not started |  | Code tidak bisa dipakai setelah revoke
SET-004 | Settings | Edit informasi perusahaan/workspace | P1 | ⬜ Not started |  | Perubahan nama, deskripsi tersimpan
SET-005 | Settings | Hanya owner yang bisa akses settings admin | P0 | ⬜ Not started |  | Member tidak bisa akses fitur admin
SET-006 | Settings | Lihat daftar anggota workspace | P1 | ⬜ Not started |  | List user dalam tenant
PRF-001 | Profile | Halaman profile tampil dengan data user | P0 | ⬜ Not started |  | Nama, email, foto profil
PRF-002 | Profile | Edit nama/info profil | P1 | ⬜ Not started |  | Perubahan tersimpan ke database
PRF-003 | Profile | Ganti password dari profil | P1 | ⬜ Not started |  | Password baru aktif setelah ganti
PRF-004 | Profile | Ganti password dengan password lama salah | P1 | ⬜ Not started |  | Error message tampil
PRF-005 | Profile | Foto profil upload & tampil | P2 | ⬜ Not started |  | Foto berhasil diupload dan ditampilkan
NOT-001 | Notification System | Notification dropdown tampil | P1 | ⬜ Not started |  | List notifikasi muncul saat diklik
NOT-002 | Notification System | Badge count notifikasi akurat | P1 | ⬜ Not started |  | Jumlah unread sesuai
NOT-003 | Notification System | Mark notifikasi sebagai read | P1 | ⬜ Not started |  | Badge berkurang, status berubah
NOT-004 | Notification System | Mark all as read berfungsi | P1 | ⬜ Not started |  | Semua notifikasi jadi read, badge hilang
NOT-005 | Notification System | Notifikasi baru muncul real-time | P0 | ⬜ Not started |  | Tanpa refresh halaman
NOT-006 | Notification System | Klik notifikasi navigasi ke event terkait | P2 | ⬜ Not started |  | Link ke halaman history/detail event
UI-001 | General UI/UX | Responsive layout di berbagai resolusi (1366x768, 1920x1080) | P1 | ⬜ Not started |  | Layout tidak broken
UI-002 | General UI/UX | Sidebar navigasi berfungsi di semua halaman | P0 | ⬜ Not started |  | Semua link navigasi aktif
UI-003 | General UI/UX | Loading spinner tampil saat fetch data | P2 | ⬜ Not started |  | UX saat menunggu data
UI-004 | General UI/UX | Error message tampil saat API gagal | P1 | ⬜ Not started |  | Toast/alert error informatif
UI-005 | General UI/UX | Toast notification sukses/error tampil & hilang otomatis | P2 | ⬜ Not started |  | Auto dismiss setelah beberapa detik
UI-006 | General UI/UX | Halaman 404 / route tidak ditemukan ditangani | P2 | ⬜ Not started |  | Redirect atau pesan not found
UI-007 | General UI/UX | Multi-tenant: data hanya dari tenant sendiri | P0 | ⬜ Not started |  | Tidak ada data cross-tenant bocor
UI-008 | General UI/UX | Dark mode / tema konsisten (jika ada) | P3 | ⬜ Not started |  | Warna dan tema konsisten

## QA To Do List
QA TESTER | Tim QA |  | APP | CCTV Dashboard Web App
DATE | 2026-06-04 |  | PLATFORM | Web Browser
Dokumen ini berisi daftar tugas (To Do) yang perlu diselesaikan oleh tim QA untuk pengujian aplikasi CCTV Dashboard Monitoring.
Setiap task memiliki prioritas, assignee, deadline, dan status tracking.
No | Task / Kegiatan QA | Kategori | Prioritas | Assignee | Deadline | Status | Keterangan
1 | Setup environment testing (staging/dev URL, akun test, browser) | Persiapan | P0 |  |  | ⬜ Not started | Siapkan minimal 2 akun: Owner dan Member
2 | Siapkan data test: minimal 1 tenant, 2 kamera, 5 identitas, 10 events | Persiapan | P0 |  |  | ⬜ Not started | Data harus ada sebelum testing dimulai
3 | Verifikasi backend & WebSocket berjalan di environment test | Persiapan | P0 |  |  | ⬜ Not started | Cek koneksi ke Supabase & backend engine
4 | Buat akun Owner baru via Sign Up untuk testing fresh flow | Persiapan | P1 |  |  | ⬜ Not started | Gunakan email testing yang bisa diakses
5 | Generate invite code dari Settings untuk testing Member signup | Persiapan | P1 |  |  | ⬜ Not started | Simpan invite code untuk test AUTH-030
6 | Jalankan semua test case Authentication - Login (AUTH-001 s/d AUTH-010) | Authentication | P0 |  |  | ⬜ Not started | 10 test cases, estimasi 1 jam
7 | Jalankan test case Sign Up Owner (AUTH-020 s/d AUTH-026) | Authentication | P0 |  |  | ⬜ Not started | Test dengan email baru setiap kali
8 | Jalankan test case Sign Up Member via Invite Code (AUTH-030 s/d AUTH-032) | Authentication | P0 |  |  | ⬜ Not started | Butuh invite code valid dari step 5
9 | Jalankan test case Forgot Password (AUTH-040 s/d AUTH-043) | Authentication | P1 |  |  | ⬜ Not started | Perlu akses email untuk cek link reset
10 | Jalankan test case Logout & Protected Route (AUTH-050 s/d AUTH-052) | Authentication | P0 |  |  | ⬜ Not started | Pastikan session benar-benar cleared
11 | Jalankan test case Live Monitoring - Streaming (MON-001 s/d MON-004) | Live Monitoring | P0 |  |  | ⬜ Not started | Pastikan minimal 1 kamera aktif streaming
12 | Jalankan test case Live Monitoring - Real-time Events (MON-005 s/d MON-008) | Live Monitoring | P0 |  |  | ⬜ Not started | Butuh kamera dengan face detection aktif
13 | Test WebSocket reconnect (MON-012) dengan cara putus koneksi internet sementara | Live Monitoring | P1 |  |  | ⬜ Not started | Simulasi disconnect selama 5-10 detik
14 | Test stability monitoring dengan 4+ kamera aktif sekaligus (MON-010) | Live Monitoring | P1 |  |  | ⬜ Not started | Monitor memory & CPU browser selama 10 menit
15 | Verifikasi tidak ada duplikasi event real-time (MON-011) | Live Monitoring | P1 |  |  | ⬜ Not started | Amati event list selama 5 menit
16 | Jalankan test case History - Display & Pagination (HIS-001, HIS-002) | Incident History | P0 |  |  | ⬜ Not started | Pastikan ada 10+ events di database
17 | Jalankan test case History - Filter & Search (HIS-003 s/d HIS-006) | Incident History | P1 |  |  | ⬜ Not started | Test semua kombinasi filter
18 | Test Review event - mark violation & compliance (HIS-008, HIS-009) | Incident History | P0 |  |  | ⬜ Not started | Pastikan status tersimpan ke database
19 | Test Export CSV (HIS-010) dan verifikasi isi file | Incident History | P1 |  |  | ⬜ Not started | Buka file CSV dan cek kelengkapan kolom
20 | Test detail event dengan foto evidence (HIS-007) | Incident History | P1 |  |  | ⬜ Not started | Foto harus ter-load dari Supabase storage
21 | Jalankan test case tambah & upload identitas (IDN-001 s/d IDN-003) | Identity Management | P0 |  |  | ⬜ Not started | Upload foto wajah yang jelas (resolusi baik)
22 | Verifikasi face encoding berhasil di-trigger setelah upload (IDN-006) | Identity Management | P0 |  |  | ⬜ Not started | Cek log backend atau status encoding
23 | Test edit dan hapus identitas (IDN-004, IDN-005) | Identity Management | P1 |  |  | ⬜ Not started | Konfirmasi dialog hapus harus muncul
24 | Test validasi upload foto format salah (IDN-009) | Identity Management | P1 |  |  | ⬜ Not started | Coba upload file PDF, TXT, GIF
25 | Test search/filter identitas (IDN-008) | Identity Management | P2 |  |  | ⬜ Not started | Cari berdasarkan nama
26 | Jalankan test case tambah kamera baru (CAM-001, CAM-002) | Camera Management | P0 |  |  | ⬜ Not started | Gunakan URL RTSP/HTTP yang valid
27 | Test start & stop stream kamera (CAM-005, CAM-006) | Camera Management | P0 |  |  | ⬜ Not started | Verifikasi status update di UI
28 | Test edit dan hapus kamera (CAM-003, CAM-004) | Camera Management | P1 |  |  | ⬜ Not started | Konfirmasi dialog hapus harus muncul
29 | Test real-time status update kamera (CAM-008) | Camera Management | P1 |  |  | ⬜ Not started | Matikan kamera fisik, cek UI berubah
30 | Test validasi URL kamera format salah (CAM-007) | Camera Management | P1 |  |  | ⬜ Not started | Masukkan URL random/tidak valid
31 | Jalankan test case Reports - Display & Filter (REP-001 s/d REP-003) | Reports | P0 |  |  | ⬜ Not started | Pastikan ada events dengan foto di database
32 | Verifikasi foto evidence ter-load dengan benar di report (REP-004) | Reports | P0 |  |  | ⬜ Not started | Cek dari Supabase Storage, bukan broken image
33 | Test pagination dan detail report (REP-005, REP-006) | Reports | P1 |  |  | ⬜ Not started
34 | Jalankan test case Settings - Invite Code (SET-002, SET-003) | Settings | P0 |  |  | ⬜ Not started | Generate, copy, dan revoke invite code
35 | Test akses kontrol Settings - hanya Owner (SET-005) | Settings | P0 |  |  | ⬜ Not started | Login sebagai Member, cek akses ditolak
36 | Test edit info perusahaan (SET-004) | Settings | P1 |  |  | ⬜ Not started | Perubahan tersimpan dan tampil
37 | Jalankan test case Profile (PRF-001 s/d PRF-005) | Profile | P1 |  |  | ⬜ Not started | Edit profil, ganti password
38 | Test notifikasi real-time (NOT-001, NOT-002, NOT-005) | Notification System | P0 |  |  | ⬜ Not started | Trigger event dari kamera, cek notifikasi muncul
39 | Test mark as read & mark all as read (NOT-003, NOT-004) | Notification System | P1 |  |  | ⬜ Not started | Badge count harus update
40 | Test responsive layout di resolusi 1366x768 dan 1920x1080 (UI-001) | General UI/UX | P1 |  |  | ⬜ Not started | Gunakan DevTools Chrome untuk simulasi
41 | Verifikasi multi-tenant isolation - data tidak bocor antar tenant (UI-007) | General UI/UX | P0 |  |  | ⬜ Not started | Login 2 tenant berbeda, pastikan data terpisah
42 | Test semua link navigasi sidebar (UI-002) | General UI/UX | P0 |  |  | ⬜ Not started | Klik setiap menu di sidebar
43 | Test error handling saat API gagal / timeout (UI-004) | General UI/UX | P1 |  |  | ⬜ Not started | Matikan internet sebentar, cek error message
44 | Test di browser Chrome, Firefox, dan Edge (cross-browser) | General UI/UX | P1 |  |  | ⬜ Not started | Jalankan smoke test di minimal 2 browser
45 | Dokumentasikan semua bug yang ditemukan dengan screenshot | Bug Documentation | P0 |  |  | ⬜ Not started | Gunakan format: BUG-XXX dengan screenshot & repro steps
46 | Buat laporan QA final setelah semua test selesai | Pelaporan | P0 |  |  | ⬜ Not started | Ringkasan: passed, failed, blocked, bug list